## Slide 1
Sprint 1 Review &
Retrospective
Travel App · DISI 2026
Augustin Sasu (Database)
Man Mihai (Backend)
Andrei Dorneanu (Backend)
Casiana Cosma (Frontend)
Andreea Anastasiu (Frontend)
Apr 7 – Apr 21, 2026

## Slide 2
Project Overview
Travel App DISI'26 — Sprint 1 Goal
42
Story Points
Committed
42
Story Points
Completed
100%
Sprint Goal
Achieved
42 SP
Team
Velocity
Database Foundation
PostgreSQL schema, init scripts & seed data (Augustin Sasu)
Backend — Auth Module
Spring Boot: security config, JWT, login & register endpoints (Andrei Dorneanu)
Backend — User Module
User profile functionality, unit & integration tests (Man Mihai)
Frontend — Setup
React + Vite bootstrap, API service layer, dependencies (Andreea Anastasiu)
Frontend — UI
Login/Register screens, Navbar, User Profile page (Casiana Cosma)

## Slide 3
Augustin Sasu — Database Foundation
SCRUM-17 · SCRUM-18
SCRUM-17 — Database Schema
Designed full PostgreSQL schema: tables, relationships, constraints & indices
Covers user management and future travel features
SQL Initialization Scripts
SQL scripts for database setup — any team member can spin up local DB from scratch
Single-command setup for consistent environments
DB Seed / Spring Initializer
DatabaseInitializer component runs on startup
Ensures schema consistency: tables, default values, test data
Problems Encountered
None — task completed on time (Apr 15)
Passed review without issues
Note: DB schema was delivered late relative to backend needs — this caused some blocking in week 1 for the backend team
What Should Be Improved
Start DB schema earlier (Day 1–2 of sprint) to unblock backend team
Define schema contract with backend before implementation
Add seed data covering edge cases for better test coverage

## Slide 4
Man Mihai — Backend Development
Security · User Profile · Testing
SCRUM-30 — Spring Security
JWT-based stateless auth, filter chain, CORS config
Public vs protected route rules
SCRUM-32 — User Profile
GET/PUT endpoints, DTO mapping, input validation
Secured so only authenticated users access own profile
SCRUM-33 & 34 — Tests
JUnit/Mockito unit tests + Spring Boot integration tests
Auth & user layers, happy-path and edge cases
Problems Encountered
SCRUM-32 briefly re-opened Apr 19 → fixed same day (3:32 pm)
Minor review issue — turnaround was fast
No major blockers; all tasks completed within sprint
What Should Be Improved
Self-review checklist before marking task 'Done' to avoid re-opens
Define OpenAPI spec upfront to reduce integration friction
Start integration tests earlier — don't leave for end of sprint
Add mobile/responsive awareness even on API layer contracts

## Slide 5
Andrei Dorneanu — Backend Development
Authentication Controller & Endpoints
SCRUM-25 — US1: User Login
Login endpoint: credential validation, JWT generation
Error handling for invalid credentials
SCRUM-29 — US2: User Register
Registration flow: input validation, BCrypt hashing
Duplicate-email check and user persistence
SCRUM-31 — US4: Auth Controller
AuthController exposing /api/auth/login and /api/auth/register
Wired to auth service layer, fully functional
Problems Encountered
All tasks completed on time, no roadblocks
Backend auth module is fully functional and tested
What Should Be Improved
Swagger/OpenAPI documentation should be published at sprint start
Work started mostly in week 2 — better to distribute across both weeks
Add refresh-token endpoint in next sprint
Error responses should follow a standardized format across all endpoints

## Slide 6
Andreea Anastasiu — Frontend Development
React Setup · Auth UI · Dependencies
SCRUM-38 — Init React + Vite
Bootstrapped React + Vite with folder structure, ESLint, env vars
SCRUM-39 — Frontend Dependencies
React Router, Axios, TailwindCSS, form/validation libraries
SCRUM-41 — Login & Register UI
Login/Register pages with form validation and error display
Connected to backend auth API endpoints
Problems Encountered
All tasks completed successfully
Login/Register UI functional and integrated with backend auth
No major blockers reported
What Should Be Improved
No mobile/responsive testing was done — add to Definition of Done
API integration started late (dependent on backend readiness)
Loading states and error UX could be more polished
Component reuse between Login and Register pages can be improved

## Slide 7
Casiana Cosma — Frontend Development
Navbar · User Profile UI · API Service Layer
SCRUM-40 — API Service Layer
Centralized Axios module with JWT interceptors
Error handling used by all frontend components
SCRUM-42 — Navigation (Navbar)
Responsive Navbar with routing, active-link highlighting
Conditional render: logged-in vs guest state
SCRUM-43 — User Profile Page
Profile page displaying user info from backend
Edit mode for updating profile details (done Apr 21)
Problems Encountered
All tasks completed successfully
SCRUM-43 finished Apr 21 (last day of sprint)
Centralized API service used across entire frontend
What Should Be Improved
Profile page finished on the last day — aim to complete 1–2 days earlier
No mobile responsiveness tested on Navbar or Profile page
Global error handling in API service should surface better UI feedback
Consider adding token-expiry handling / auto-logout in Sprint 2

## Slide 8
Sprint 1 Process Review
What went well · What to improve · Commitments for Sprint 2
✔ What Worked Well
All 42 story points delivered — 100% sprint goal achieved
Good Jira usage: tasks tracked, burndown updated
Backend & frontend decoupled via REST API contract
Git branching (feature/SCRUM-XX) followed consistently
Merge requests used with peer review before merge
✗ What Could Be Improved
Late start: most work in week 2 (Apr 14–21), not week 1
DB schema delivered late — blocked backend in week 1
No OpenAPI/Swagger contract upfront — integration delays
One task re-opened (SCRUM-32) — review process needs tightening
No mobile/responsive testing for any UI component
🎯 Sprint 2 Commitments
Define & publish OpenAPI spec at sprint start
DB schema + seed data ready by Day 2
Mobile responsiveness in Definition of Done
Self-review checklist before marking 'Done'
Distribute work evenly across week 1 & 2

## Slide 9
Team Velocity
Sprint 1 — Story Points Burned
42
Story Points
Committed
42
Story Points
Completed
100%
Sprint Goal
Achieved
42 SP
Team
Velocity
Chart: 
| Week 1 (Apr 7–14) | Week 2 (Apr 15–21)
Story Points | 6 | 36
Note: Work started late (Apr 15). Most story points burned in week 2. All 42 SP completed.